## Sheet1
Name | Duration | Start | Finish | Predecessors |  | Actual Start | Actual Finish
IDEA Cellular - CLICK PSS™ Implementation | 117 days | 2015-05-27 08:00 | 2015-11-05 17:00 |  | Planned End date | Wed 5/27/15 | NA | Dependency | Remarks
Project Kick-off (Milestone) | 1 day | 2015-05-27 08:00 | 2015-05-27 17:00 |  |  | Wed 5/27/15 | Wed 5/27/15
Requirements (Milestone) | 64 days | 2015-05-27 08:00 | 2015-08-24 17:00 |  |  | Wed 5/27/15 | Mon 8/24/15
Business Objective | 1 day | 2015-05-27 08:00 | 2015-05-27 17:00 |  |  | Wed 5/27/15 | Wed 5/27/15
Workshop for requirement Gathering | 4 days | 2015-06-18 08:00 | 2015-06-23 17:00 | 1900-01-03 |  | Thu 6/18/15 | Tue 6/23/15
Product walkthrough | 1 day | 2015-06-18 08:00 | 2015-06-18 17:00 |  |  | Thu 6/18/15 | Thu 6/18/15 | Workshop for requirement Gathering
Eliciting the Business Requirement | 0 days | 2015-06-18 08:00 | 2015-06-18 08:00 | 1900-01-05 | 2015-11-10 | Thu 6/18/15 | Thu 6/18/15 | Product walkthrough
Sharing the BRD document | 0 days | 2015-06-23 17:00 | 2015-06-23 17:00 |  | 0 | Tue 6/23/15 | Tue 6/23/15 | Eliciting the Business Requirement
System Requirement Specification (SRS) Gathering | 46 days | 2015-06-22 08:00 | 2015-08-24 17:00 | 1900-01-04 |  | Mon 6/22/15 | Mon 8/24/15
Sharing the input and other IT project details | 6 days | 2015-06-25 08:00 | 2015-07-02 17:00 |  | 1900-01-01 | Thu 6/25/15 | Thu 7/2/15
Requirement Gathering | 46 days | 2015-06-22 08:00 | 2015-08-24 17:00 | 1900-01-09 | 1900-01-01 | Mon 6/22/15 | Mon 8/24/15
Input | 43 days | 2015-06-25 08:00 | 2015-08-24 17:00 |  |  | Thu 6/25/15 | Mon 8/24/15
Database details, table scripts, sample data, db queries / mapping info | 26 days | 2015-06-25 08:00 | 2015-07-30 17:00 |  |  | Thu 6/25/15 | Thu 7/30/15
Sharing of all the creative / marketing materials such as logo, advt images, fonts, etc. | 43 days | 2015-06-25 08:00 | 2015-08-24 17:00 |  |  | Thu 6/25/15 | Mon 8/24/15 | Sharing the BRD document
Output | 21 days | 2015-07-02 08:00 | 2015-07-30 17:00 |  | 1900-01-06 | Thu 7/2/15 | Thu 7/30/15
Proposed Bill layouts (Final output as required) - Individual & Multi contracts (Retail and Corporate) | 21 days | 2015-07-02 08:00 | 2015-07-30 17:00 |  | 1900-01-06 | Thu 7/2/15 | Thu 7/30/15
Preparing the SRS document | 0 days | 2015-06-22 08:00 | 2015-07-30 17:00 | 12,15 | 1900-01-06 | Mon 6/22/15 | Thu 7/30/15
SRS Sign off | 0 days | 2015-07-03 08:00 | 2015-08-11 17:00 | 1900-01-16 | 1900-01-06 | Fri 7/3/15 | Tue 8/11/15 | 14-16
Server procurement and setup with pre-requisites (Milestone) | 68 days | 2015-05-27 08:00 | 2015-08-28 17:00 |  | 1899-12-31 | Wed 5/27/15 | Fri 8/28/15 | SRS Sign off
Development machines | 1 day | 2015-05-27 08:00 | 2015-05-27 17:00 |  | 0 | Wed 5/27/15 | Wed 5/27/15 | Server procurement and setup with pre-requisites (Milestone)
Test Server | 1 day | 2015-05-27 08:00 | 2015-05-27 17:00 |  |  | Wed 5/27/15 | Wed 5/27/15
SIT Server | 1 day | 2015-05-27 08:00 | 2015-05-27 17:00 |  | 1900-01-29 | Wed 5/27/15 | Wed 5/27/15 | 19
UAT Server | 1 day | 2015-05-27 08:00 | 2015-05-27 17:00 |  | 1900-01-08 | Wed 5/27/15 | Wed 5/27/15
Production Server | 1 day | 2015-05-27 08:00 | 2015-05-27 17:00 |  | 1900-01-02 | Wed 5/27/15 | Wed 5/27/15 | 21-22
Application | 1 day | 2015-05-27 08:00 | 2015-05-27 17:00 |  | 1899-12-31 | Wed 5/27/15 | Wed 5/27/15 | 23
Database | 1 day | 2015-05-27 08:00 | 2015-05-27 17:00 |  | 0 | Wed 5/27/15 | Wed 5/27/15 | Production Server
Installation | 1 day | 2015-08-27 08:00 | 2015-08-27 17:00 | 24,3 |  | Thu 8/27/15 | Thu 8/27/15
Pre-requisites | 1 day | 2015-08-27 08:00 | 2015-08-27 17:00 |  | 1900-01-03 | Thu 8/27/15 | Thu 8/27/15 | 24-25
Oracle Installation - UAT & Production | 1 day | 2015-08-27 08:00 | 2015-08-27 17:00 |  | 1900-01-03 | Thu 8/27/15 | Thu 8/27/15 | 27
Testing of configured and installed hadware and application | 1 day | 2015-08-27 17:00 | 2015-08-28 17:00 | 1900-01-26 | 1900-02-05 | Thu 8/27/15 | Fri 8/28/15 | 27-28
Development - offsite activity (Milestone) | 56 days | 2015-07-10 08:00 | 2015-09-25 17:00 | 1900-01-02 | 1900-02-05 | Fri 7/10/15 | Fri 9/25/15 | 29
Database Activity | 20 days | 2015-07-10 08:00 | 2015-08-06 17:00 |  | 0 | Fri 7/10/15 | Thu 8/6/15 | 29-30
Database schema creation | 10 days | 2015-07-10 08:00 | 2015-07-23 17:00 |  |  | Fri 7/10/15 | Thu 7/23/15 | 31
CLICK PSS As is Repository creation | 1 day | 2015-07-10 08:00 | 2015-07-10 17:00 |  |  | Fri 7/10/15 | Fri 7/10/15
CLICK PSS Customization for Idea specific requirement | 5 days | 2015-07-13 08:00 | 2015-07-17 17:00 | 1900-02-02 | 1900-02-02 | Mon 7/13/15 | Fri 7/17/15 | 33
Updating Procedures for Idea specific requirement | 4 days | 2015-07-20 08:00 | 2015-07-23 17:00 | 1900-02-03 | 1900-02-03 | Mon 7/20/15 | Thu 7/23/15 | 34
Extraction & Loading (Parsing) | 10 days | 2015-07-24 08:00 | 2015-08-06 17:00 |  | 0 | Fri 7/24/15 | Thu 8/6/15 | 35
Extraction of data from Text files to DB to XML | 10 days | 2015-07-24 08:00 | 2015-08-06 17:00 |  |  | Fri 7/24/15 | Thu 8/6/15
Individual Contracts (Retail) | 5 days | 2015-07-24 08:00 | 2015-07-30 17:00 |  |  | Fri 7/24/15 | Thu 7/30/15
Multi Contracts (Corporate) | 5 days | 2015-07-31 08:00 | 2015-08-06 17:00 | 39 |  | Fri 7/31/15 | Thu 8/6/15
Statement Designing | 8 days | 2015-08-03 08:00 | 2015-08-12 17:00 |  |  | Mon 8/3/15 | Wed 8/12/15
Individual Contracts (Retail) | 7 days | 2015-08-03 08:00 | 2015-08-11 17:00 |  |  | Mon 8/3/15 | Tue 8/11/15
Multi Contracts (Corporate) | 1 day | 2015-08-03 08:00 | 2015-08-12 17:00 | 42 |  | Mon 8/3/15 | Wed 8/12/15
Configuring statements with CLICKPSS App Server | 3 days | 2015-08-12 08:00 | 2015-08-14 17:00 | 41 |  | Wed 8/12/15 | Fri 8/14/15
Individual Contracts (Retail) | 3 days | 2015-08-12 08:00 | 2015-08-14 17:00 |  |  | Wed 8/12/15 | Fri 8/14/15
Multi Contracts (Corporate) | 3 days | 2015-08-12 08:00 | 2015-08-14 17:00 |  |  | Wed 8/12/15 | Fri 8/14/15
MIS / logs for reconciliation | 0 days | 2015-08-12 08:00 | 2015-08-14 17:00 | 44 |  | Wed 8/12/15 | Fri 8/14/15
External Integration with CLICK PSS | 1 day | 2015-09-25 08:00 | 2015-09-25 17:00 | 47 |  | Fri 9/25/15 | Fri 9/25/15
Email Server | 1 day | 2015-09-25 08:00 | 2015-09-25 17:00 |  |  | Fri 9/25/15 | Fri 9/25/15
CLICK PSS™ Portal Customizations | 0 days | 2015-09-25 08:00 | 2015-09-25 08:00 | 48 |  | Fri 9/25/15 | Fri 9/25/15
Bounce Trapper | 0 days | 2015-09-25 08:00 | 2015-09-25 08:00 |  |  | Fri 9/25/15 | Fri 9/25/15
SIT (Milestone) | 40 days | 2015-08-17 08:00 | 2015-10-09 17:00 | 31 |  | Mon 8/17/15 | Fri 10/9/15
Deployment on SIT Server (offsite activity) | 6 days | 2015-08-17 08:00 | 2015-08-24 17:00 |  |  | Mon 8/17/15 | Mon 8/24/15
System Testing by Idea | 18 days | 2015-09-07 08:00 | 2015-09-30 17:00 |  |  | Mon 9/7/15 | Wed 9/30/15
Cycle 1 | 10 days | 2015-09-07 08:00 | 2015-09-18 17:00 |  |  | Mon 9/7/15 | Fri 9/18/15
System Testing Cycle 1 | 7 days | 2015-09-07 08:00 | 2015-09-15 17:00 |  |  | Mon 9/7/15 | Tue 9/15/15
Defect fixes | 3 days | 2015-09-15 08:00 | 2015-09-18 17:00 | 56 |  | Tue 9/15/15 | Fri 9/18/15
Cycle 2 | 9 days | 2015-09-18 08:00 | 2015-09-30 17:00 | 55 |  | Fri 9/18/15 | Wed 9/30/15
System Testing Cycle 2 | 6 days | 2015-09-18 08:00 | 2015-09-25 17:00 |  |  | Fri 9/18/15 | Fri 9/25/15
Defect fixes | 3 days | 2015-09-25 08:00 | 2015-09-30 17:00 | 59 |  | Fri 9/25/15 | Wed 9/30/15
Regression and Report | 1 day | 2015-10-01 08:00 | 2015-10-01 17:00 | 58 |  | Thu 10/1/15 | Thu 10/1/15
System Test Closure & SIT Sign off | 5 days | 2015-10-05 08:00 | 2015-10-09 17:00 | 58 |  | Mon 10/5/15 | Fri 10/9/15
Training - Session 1 | 1 day | 2015-10-12 08:00 | 2015-10-12 17:00 | 52 |  | Mon 10/12/15 | Mon 10/12/15
User Acceptance Testing (UAT) (offsite - remote server access) (Milestone) | 21 days | 2015-09-25 08:00 | 2015-10-23 17:00 | 63 |  | Fri 9/25/15 | Fri 10/23/15
Deployment on UAT Server | 1 day | 2015-09-25 08:00 | 2015-09-25 17:00 |  |  | Fri 9/25/15 | Fri 9/25/15
Execute UAT on all Modules | 9 days | 2015-10-01 08:00 | 2015-10-13 17:00 | 65 |  | Thu 10/1/15 | Tue 10/13/15
Cycle 1 | 7 days | 2015-10-01 08:00 | 2015-10-09 17:00 |  |  | Thu 10/1/15 | Fri 10/9/15
Conduct UAT Cycle 1 | 7 days | 2015-10-01 08:00 | 2015-10-09 17:00 |  |  | Thu 10/1/15 | Fri 10/9/15
Carry out defect management / Bug Fixes | 2 days | 2015-10-08 08:00 | 2015-10-09 17:00 | 68 |  | Thu 10/8/15 | Fri 10/9/15
Cycle 2 | 2 days | 2015-10-12 08:00 | 2015-10-13 17:00 | 67 |  | Mon 10/12/15 | Tue 10/13/15
Conduct UAT Cycle 2 | 2 days | 2015-10-12 08:00 | 2015-10-13 17:00 |  |  | Mon 10/12/15 | Tue 10/13/15
Provide test summary reports | 1 day | 2015-10-14 08:00 | 2015-10-14 17:00 | 70 |  | Wed 10/14/15 | Wed 10/14/15
UAT Sign-Off | 1 day | 2015-10-23 08:00 | 2015-10-23 17:00 | 70 |  | Fri 10/23/15 | Fri 10/23/15 | 2016-01-05 | UAT signoff ( leaving bounce trapper
IT Security | 5 days |  |  | 64 |  |  |  |  | Compliance integration unit for Connection using SFTP connection
IT Security testing - Round 1 | 1 day
Fixing observations if any | 2 days |  |  | 75
IT Security testing - Round 2 | 1 day |  |  | 76
IT Security - Sign off | 1 day |  |  | 77
Training - Session 2 | 1 day |  |  | 74
Deployment of Application on Production Server (Milestone) | 2 days |  |  | 79
Transition & Go-Live | 2 days
System Change Management Process | 2 days
Prerequisite - Check OS version, Oracle Version, etc | 2 days
Transport the DB to the new database | 2 days
Complete clean up of production DB server | 2 days
Final Sanity Check | 2 days
Sign- Off on Live Migration | 2 days
Golive (Milestone) | 1 day |  |  | 80